## Project Summary
13:09
Project Summary (read-only)
| Project Name | 無題のスプレッドシート
| Project Manager | ichikawa.s.417@gmail.com
| Start date | 2019-07-01
| Finish date | 2019-07-31
| Days | 23
| Progress | 17.69%
| Work hours | Pro
| Remaining work hours | Pro
| Remaining work days | Pro
| Remaining weeks | Pro
Cost

## Task Schedule
[10 empty] | June 2019 | [6 empty] | July 2019 | [30 empty] | August 2019
WBS | Task description | Start date | Finish date | Days | Link | Progress | Resources | Work hours | Cost | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1
wbs | task | start | finish | duration | link | progress | resources | work | cost | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | #
¦
1 | 機能一覧 | 2019-07-01 | 2019-07-02 | 2 |  | 100% | [10 empty] | = | = |  |  |  | ¦
2 | UI Flows | 2019-07-04 | 2019-07-04 | 1 |  | 100% | [13 empty] | = |  | ¦
3 | ワイヤーフレーム | 2019-07-05 | 2019-07-05 | 1 |  | 70% | [14 empty] | = | ¦
4 | ER図 | 2019-07-07 | 2019-07-09 | 2 |  | 30% | [15 empty] | ¦ | =
5 | テーブル定義書 | 2019-07-10 | 2019-07-10 | 1 |  | 0% | [15 empty] | ¦
6 | アプリケーション詳細設計書 | 2019-07-11 | 2019-07-11 | 1 |  | 0% | [15 empty] | ¦
7 | 実装 | 2019-07-13 | 2019-07-22 | 6 |  | 0% | [15 empty] | ¦
8 | テスト | 2019-07-23 | 2019-07-26 | 4 |  | 0% | [15 empty] | ¦
9 | プレゼン準備 | 2019-07-27 | 2019-07-27 | 0 |  | 0% | [15 empty] | ¦
10 | プレゼン | 2019-07-30 | 2019-07-31 | 2 |  | 0% | [15 empty] | ¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦

## Resources
Resource name | Type | Rate per resource | Total count | Total cost
resource | type | rate | count | cost

## Holidays
Non-working dates | Description

## TRANSGOOGLE (hidden)
translate (contact in English please) | 翻訳する（英語で連絡してください）